## weekly-sprint
Weekly Sprint
Yet to be Assigned
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Server Interaction |  | Reporting Presentations/Posts, Account creation in the LoginScene, Log in with username and password in LoginScene, Uploading post to server, Get appropriate map from server, storing it in temp folder, Get posts from server, Implement exportToXML method for Presentation |  |  | Not Written | 7
Subitems | Name | Owner | Status | Time Est. | Date
Reporting Presentations/Posts
Account creation in the LoginScene
Log in with username and password in LoginScene
Uploading post to server
Get appropriate map from server, storing it in temp folder
Get posts from server
Implement exportToXML method for Presentation
After Contract Return |  | Test returned code, Extend Presentation XML parser to create the new objects in the presentation |  |  | Not Written | 2
Subitems | Name | Owner | Status | Time Est. | Date
Test returned code
Extend Presentation XML parser to create the new objects in the presentation
SpT - Week 2/3
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Visually implement options scene | Sarujan Thevathasan, Oli Partidge |  |  | Done | Not Written | 2
visually create open sidebar scene | Jonathan Cooke, jwh535@york.ac.uk |  |  | Working on it | Not Written | 2
Visually implement UploadScene | Fraser Todd, Sophie |  |  | Done | Not Written | 2
create loginScene visually | Srikanth Jakka, Luke George |  |  | Working on it | Not Written | 2
Initial server initialisation and Spring Security configuration | Sidharth Shanmugam |  |  | Done | Pass | 1
Server 'user' entity and unit tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1
SpT - Week 4
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
PresElement | Fraser Todd |  |  | Done | Pass | 0.25
MediaElement | Fraser Todd |  |  | Done | Pass | 1.5 | https://sweng-project-team.monday.com/boards/3597267260/pulses/3893781790
PlayableMediaElement | Fraser Todd |  |  | Done | Pass | 0.25 | MediaElement: https://sweng-project-team.monday.com/boards/3597267260/pulses/3893783030
Slide class | Fraser Todd |  |  | Done | Pass | 0.25 | PresElement Class
Presentation Class | Fraser Todd |  |  | Done | Pass | 0.25 | Slide class
implement image viewer class | Luke George, Srikanth Jakka |  |  | Working on it | Not Written | 2 | Slide class
implement videoPlayer class | Matteo Pearce, jwh535@york.ac.uk |  |  | Done | Pass | 2 | Slide class
implement audioPlayer class | Sarujan Thevathasan, Oli Partidge |  |  | Working on it | Not Written | 2 | Slide class
Server 'user' repository and Spring JPA tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 2
SpT - Week 5
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
implement contruction of a Presentation from an XML file | Fraser Todd |  |  | Done | Mixed - see comments | 3
Create enum type for colour pallet |  |  |  |  | Not Written | 0.5
integrate media package |  |  |  |  | Not Written | 1
fix issues with OptionsScene |  | make it a JPanel, Refactor class name to have a capital letter, make setup private/move it into the constructor since it will only be called there, add action listener to each button which calls overrideable public functions on button press |  | Done | Not Written | 2
Subitems | Name | Owner | Status | Time Est. | Date
make it a JPanel
Refactor class name to have a capital letter
make setup private/move it into the constructor since it will only be called there
add action listener to each button which calls overrideable public functions on button press
Update login screen to visually resemble the mock ups | Sophie |  |  | Done | Not Written | 1
implement mapScene visually | Fraser Todd |  |  | Done | GUI not tested | 1
implement PostMarker class | Fraser Todd |  |  | Done | Pass | 0.5
implement Heatmap class | Fraser Todd |  |  | Done | GUI not tested | 0.5
Server 'role' entity and unit tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1
Server 'role' repository and Spring JPA tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1
Server 'map' entity and unit tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1
Server 'map' repository and Spring JPA tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1
Server 'media' entity and unit tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1 |  | 2023-02-08
Server 'media' repository and Spring JPA tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1 |  | 2023-02-08
2023-02-08
SpT - Week 6
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Server 'post' entity and unit tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1
Server 'post' repository and Spring JPA tests | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1
Server 'user' entity refactoring and testing with 'role' and 'post' models | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1
Server 'user' implementation and implementation testing | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 2
Server 'role' implementation and implementation testing | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1.5
Server 'post' implementation and implementation testing | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1.5
Server 'media' implementation and implementation testing | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1.5
Server 'map' implementation and implementation testing | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1.5
fix issues with SidebarScene & implement Presentations within it | Fraser Todd | minimize makes the whole scene dissapear, when it should only make the presentations disappear, leaving the button and text field, The test seems to give several warnings, make the addPres test not fail, View presentations within a list in the sidebar | Medium | Done | Pass | 2
Subitems | Name | Owner | Status | Time Est. | Date
| minimize makes the whole scene dissapear, when it should only make the presentations disappear, leaving the button and text field | Sophie | Done
The test seems to give several warnings
make the addPres test not fail
View presentations within a list in the sidebar
fix issues with UploadScene (will extend to week 7) |  | Bottom buttons to replicate the mockup, Tabbar and Slide screen to be integrated to a JTabbedPane, Custom TabbedPaneUI could be made to replicate this look, Integrate text fields where appropriate, accept drag and dropped files into media bar on the left, implement the tag box, implement the location box in the top right |  |  | Not Written | 7
Subitems | Name | Owner | Status | Time Est. | Date
| Bottom buttons to replicate the mockup | Sophie | Done
| Tabbar and Slide screen to be integrated to a JTabbedPane | Sophie | Done
| Custom TabbedPaneUI could be made to replicate this look | Sophie | Done
| Integrate text fields where appropriate | Sophie | Done
| accept drag and dropped files into media bar on the left | Sophie | Done
| implement the tag box | Sophie | Done
implement the location box in the top right
CONTRACT -> implement text for android (more detail to come) | Sophie |  |  | Done | Pass | 2
CONTRACT -> implement images for android |  |  |  |  | Not Written | 2
SpT - Week 7
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Server authentication and Spring Security Configuration | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 1
Server 'get/post/delete map' API endpoint and endpoint testing | Sidharth Shanmugam, Paul Pickering |  |  | Done | Pass | 3
Server 'post/get/delete media' API endpoint and endpoint testing | Sidharth Shanmugam, Paul Pickering |  |  | Waiting for review | Not Written | 4
Server 'post/get/delete user' API endpoint and endpoint testing | Sidharth Shanmugam, Paul Pickering |  |  | Waiting for review | Not Written | 4
Integrate the "SceneControl" package allowing the creation of MainScene |  |  |  |  | Not Written
Create MainScene populating it with the other scenes |  |  |  |  | Not Written | 2
CONTRACT -> implement text for android CONTRACT -> implement text for android (more detail to come) | Sophie |  |  | Done | Pass | 2
CONTRACT -> implement images for android CONTRACT -> implement text for android (more detail to come) |  |  |  | Done | Pass | 2
SpT - Week 8
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Server 'get/post/delete post - logged out user' API endpoint and endpoint testing | Sidharth Shanmugam, Paul Pickering |  |  | Waiting for review | Not Written | 2
Server 'get/post/delete post - logged in user' API endpoint and endpoint testing | Sidharth Shanmugam, Paul Pickering |  |  | Waiting for review | Not Written | 2
Server 'get/post/delete post - organisational user' API endpoint and endpoint testing | Sidharth Shanmugam, Paul Pickering |  |  | Waiting for review | Not Written | 2
SpT - Week 9
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Client ''MainScene" Code Coverage and Integration Testing |  |  |  |  | Not Written | 1.5
Client ''MainScene" Code Coverage and Integration Fixes |  |  |  |  | Not Written | 1.5
Client ''MapScene" Code Coverage and Integration Testing |  |  |  |  | Not Written | 1.5
Client ''MapScene" Code Coverage and Integration Fixes |  |  |  |  | Not Written | 1.5
Client ''LoginScene" Code Coverage and Integration Testing |  |  |  |  | Not Written | 1.5
Client ''LoginScene" Code Coverage and Integration Fixes |  |  |  |  | Not Written | 1.5
SpT - Week 10
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Client ''OptionScene" Code Coverage and Integration Testing |  |  |  |  | Not Written | 1.5
Client ''OptionScene" Code Coverage and Integration Fixes |  |  |  |  | Not Written | 1.5
Client ''UploadScene" Code Coverage and Integration Testing |  |  |  |  | Not Written | 1.5
Client ''UploadScene" Code Coverage and Integration Fixes |  |  |  |  | Not Written | 1.5
Client ''SidebarScene" Code Coverage and Integration Testing |  |  |  |  | Not Written | 1.5
Client ''SideBarScene" Code Coverage and Integration Fixes |  |  |  |  | Not Written | 1.5
SuT - Week 1
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Server-Client Integration Testing Spikes |  |  |  |  | Not Written | 5
Server-Client "Login" Endpoint Integration Tests |  |  |  |  | Not Written | 2
Server-Client "Login" Endpoint Integration Fixes |  |  |  |  | Not Written | 2
Server-Client "Refresh Token" Endpoint Integration Tests |  |  |  |  | Not Written | 1
Server-Client "Refresh Token" Endpoint Integration Fixes |  |  |  |  | Not Written | 2
SuT - Week 2
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Server-Client "Upload Map" Endpoint Integration Tests |  |  |  |  | Not Written | 2
Server-Client "Upload Map" Endpoint Integration Fixes |  |  |  |  | Not Written | 2
Server-Client "Get Map" Endpoint Integration Tests |  |  |  |  | Not Written | 1
Server-Client "Get Map" Endpoint Integration Fixes |  |  |  |  | Not Written | 2
Server-Client "Delete Map" Endpoint Integration Tests |  |  |  |  | Not Written | 0.5
Server-Client "Delete Map" Endpoint Integration Fixes |  |  |  |  | Not Written | 0.5
Server-Client "Upload Media" Endpoint Integration Tests |  |  |  |  | Not Written | 2
Server-Client "Upload Media" Endpoint Integration Fixes |  |  |  |  | Not Written | 2
SuT - Week 3
Name | Owner | Subitems | Priority | Status | Testing | Time Est. | Dependancies | Date
Server-Client "Get Media" Endpoint Integration Tests |  |  |  |  | Not Written | 1
Server-Client "Get Media" Endpoint Integration Fixes |  |  |  |  | Not Written | 2
Server-Client "Delete Media" Endpoint Integration Tests |  |  |  |  | Not Written | 0.5
Server-Client "Delete Media" Endpoint Integration Fixes |  |  |  |  | Not Written | 0.5
Server-Client "Upload Post" Endpoint Integration Tests |  |  |  |  | Not Written | 2
Server-Client "Upload Post" Endpoint Integration Fixes |  |  |  |  | Not Written | 2
Server-Client "Get Post" Endpoint Integration Tests |  |  |  |  | Not Written | 3
Server-Client "Get Post" Endpoint Integration Fixes |  |  |  |  | Not Written | 2
Server-Client "Delete Post" Endpoint Integration Tests |  |  |  |  | Not Written | 0.5
Server-Client "Delete Post" Endpoint Integration Fixes |  |  |  |  | Not Written | 0.5