## OVERVIEW
Group 1 Timesheet

## Jonathan
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | Testing SidebarScene and Media branches | Individual Work | Development Testing | 2 | 2
Week 21 | Documentation maintenance | Individual Work | Documentation | 2 | 2 | Developing a document tracker and assessing quality of commenting in source code
Week 22 | Tender Presentation | Meeting | Marketing | 1.5 | 1.5
Week 22 | QA Manual 1.4 and FS 1.1.0 | Individual Work | Documentation | 1 | 3 | Planned to just update formatting and branding, project changes required adding more user stories and user verification detail to Functional Specification
Week 22 | Testing and Integration Plan Initial Meeting | Meeting | Integration and Testing | 1 | 1
Week 22 | SidebarScene and Media branches development | Individual Work | Development - Client Software | 2 | 2
Week 24 | Sidebar Scene development | Individual Work | Development - Client Software | 1 | 1 | Focusing on improving Sidebar layout
Week 24 | Sidebar Scene Testing | Individual Work | Development Testing | 1 | 1
Week 24 | Documentation maintenance | Individual Work | Documentation | 1 | 1 | Planning for first iteration delivery, tracking documentation progress
Week 25 | SideBarScene Refactoring and Appearance for first iteration | Individual Work | Development - Client Software | 6 | 12 | More time taken than anticipated to merge code from different developers. Extra time was required to understand, comment and restructure code before merging. Required to learn new systems within Swing for custom UI design.
Week 25 | First Iteration Demonstration | Meeting | Documentation | 1 | 0.5 | Meeting lasted 30 mins only out of hour set aside
Week 25 | First Iteration Documentation Preparation and Delivery | Individual Work | Documentation | 2 | 3.5 | Decided to expand upon materials to have a more comprehensive record of the end of the iteration
Week 25 | Testing and Integration Plan Report Formatting | Individual Work | Documentation | 2 | 1 | Quick formatting changes to improve appearance and layout, proof-reading and minor error correction, less review required than anticipated due to high quality of team contributions
Week 30 | Preparation for Iteration 2 kick-off meeting | Individual Work | Documentation | 0.5 | 0.5 | Review of state of documentation and review of state of code
Week 30 | Second Iteration Kick-Off Leadership Meeting | Meeting | Documentation | 1 | 1.5 | Meeting overran due to quanity of items needing discussion
Week 30 | Document Maintenance | Individual Work | Documentation | 1 | 1 | Meeting minutes and general documentation review
Week 31 | QA Manual Documentation Review | Individual Work | Documentation | 2 | 3 | More extensive review required than anticipated.
Week 31 | Formatting Server Documentation | Individual Work | Documentation | 1 | 1
Week 34 | Final Financial Report Meeting | Meeting | Finance | 2 | 2 | Discussed role restructuring, hours costing for iteration 3
Week 34 | User Manual Writing | Individual Work | Documentation | 2 | 2 | Created a LaTeX template with section headings. Could not complete further work due to lack of a current functioning app build from which to derive plans for figures.
Week 35 | Group Project Meeting | Meeting | Documentation | 1 | 2 | Meeting overran due to additional discussion required
Week 35 | Review of Documentation Progress, Planning for Final Deliverables | Individual Work | Documentation | 2 | 2 | Discussed restructuring of Google Drive, code refactoring and approaches for final presentation and deliverables
Week 35 | Google Drive Restructure, HTML Tour Documentation Layout | Individual Work | Documentation | 8 | 6 | Reviewed all directories and files in the Google Drive and compared to deliverable requirements to determine a plan to unify the restructure with the requirements for the HTML Tour and final hand-in
Week 35 | Hand-in deliverables and code documentation | Individual Work | Documentation | 8 | 8 | Final Financial Report Review, HTML Tour Repo set up & review, Creation of exemplar code commenting file
| User Manual Writing | Individual Work | Documentation | 1 | 1
Week 35 | HTML Tour and User Manual Writing | Individual Work | Documentation | 4 | 4
Week 35 | HTML Tour and User Manual Writing | Individual Work | Documentation | 4 | 4
Week 36 | User Manual Writing and XML Test Presentation Prep | Individual Work | Documentation | 8 | 6
Week 36 | User Manual Writing/Review and HTML Tour Improvements | Individual Work | Documentation | 8 | 6 | User Manual nearly completed, HTML Tour now just needs client app images and documents, though other improvements to text could be made.
Week 36 | Reviewing the current state of the UIElementsRefactor branch | Individual Work | Development - Client Software | 0.5 | 0.5 | Checked event listener methods, to see if there was a more efficient way of writing, determined the current implementation is good. Seeing if commenting standards are being upheld.
Week 36 | HTML Tour Visuals | Individual Work | Documentation | 0.25 | 0.25 | Improved the look of the YUSU Logo on the testimonials screen
Week 36 | Photography Session | Meeting | Marketing | 1 | 1 | Took part in the photoshoot for marketing the company in the presentation and on the HTML Tour
Week 36 | Refactoring SidebarScene | Individual Work | Development - Client Software | 2 | 2 | Refactoring the Sidebar Scene to make the code more efficient and improve functionality. Working on a solution to animation problems during Maximisation and Minimisation of the Sidebar. Also pulled the most recent map render engine from Main.
Week 36 | UIElementsRefactor additions to SidebarScene and branch management | Individual Work | Development - Client Software | 3 | 3 | Experienced issues whilst refactoring UIElementsRefactor, merging work from multiple people resulted in corruption of the branch. Extra time taken to resolve the branch issues before continuing. No solution found to the animation problem.
Week 36 | sidebarSearch | Individual Work | Development - Client Software | 1.25 | 1.25 | Created a new branch for integration of the server test functions with the sidebar. Created a method which can call server methods and return presentations.
Week 36 | sidebarSearch | Individual Work | Development Testing | 1.25 | 1.25 | Wrote a test file containing a JUnit test for the new method.
Week 36 | Presentation Rehearsal | Meeting | Documentation | 1 | 0.5 | Provided feedback on the rehearsal for the Final Presentation
Week 36 | LoginScene refactor | Individual Work | Development - Client Software | 3 | 5 | Added appropriate inner and anonymous classes for UI objects to make maintenance and expansion easier. Should now be ready to implement a createAcount screen.
Week 36 | Setting up a presentation making template, finishing search function | Individual Work | Development - Client Software | 1 | 1 | Had been working on SidebarScene, however, it was decided that progress was too difficult and the Software Manager decided to do a full rewrite of the class. This rendered some of my earlier work obsolete, but I was able to use my experience to advise in pair programming.
Week 36 | Testing search function and interface | Individual Work | Development Testing | 1 | 0.5 | Was unable to complete tests due to the server not being available. Should be able to complete tomorrow. Tests are still too sparse, difficult to verify any performance as is
Week 36 | Client-server integration, XML presentation scripting, GUI improvements | Individual Work | Development - Client Software | 8 | 8 | User Interface improvements, improved the icon for the AudioPlayer visual element. Worked out how to specify graphics using the XML. Working with the Software Manager I assisted in integrating the server and client software to make the UIElementsRefactor branch ready for the final presentation demo. This included writing XML posts, squashing bugs and realising that we never included a way for users to log out of the server.
Week 37 | Group Final Sales Presentation | Meeting | Documentation | 1 | 1.25 | Time included some rehearsal as well as the presentation and Q and A session
Week 37 | Planning for final hand in | Individual Work | Documentation | 3 | 3 | Reviewed the project specification and wrote a Google Doc and Google Sheets document planning the tasks required for hand in, that could be used to track progress and ensure delivery of all required deliverables
Week 37 | User Manual Writing, Documentation Preparation for hand-in | Individual Work | Documentation | 8 | 10 | Coordinated group for hand-in tasks, wrote server installation, account creation, and XML post writing sections of the user manual. Added the PWS to the shared drive and formatted for delivery. Prepared XML presentations to be sent to Group 2. Added Oli's code commenting to the codebase. Generally spent a lot of time answering people's questions about various aspects of hand-in tasks. Assisted in Functional Specification review. Learnt even more about LaTeX. Set up a gmail account for AppBar Ltd.
Week 37 | QA Manual Review | Individual Work | Documentation | 3 | 6 | Rewrote part of the Documentation Manager Section of the QA Manual, most changes were to remove
Week 37 | FS Review | Individual Work | Documentation | 0.5 | 0.5 | Reviewed Sid's changes to the FS
Week 37 | User Manual Review | Individual Work | Documentation | 0.5 | 1 | Finalised user manual sections and figures
Week 37 | Meeting Minutes Review | Individual Work | Documentation | 0.5 | 0.5 | Added appropriate file names for minutes and sorted into appropriate folders, added the record of project manager updates
Week 37 | Preparation of example presentations | Individual Work | Development - Client Software | 1 | 1 | Compiled presentation XMLs from the final sales presentation
Week 37 | Preparing GDrive documents for HTML Tour submission | Individual Work | Documentation | 1 | 3 | Many more documents required to prepare than expected, file names and authorship added where required
Week 37 | Assisting in completion of the HTML Tour for final submission | Individual Work | Documentation | 1 | 1 | All documentation linked to the HTML Tour and final submission completed.

## List of Elapsed Weeks (hidden)
Week 33
Week 34
Week 35
Week 36
Week 37

## Luke
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | Created the Post-FBP Timesheet | Individual Work | Finance | 3 | 5.25 | Took most of the day due to self-education on Google Sheets functionality being required in order to fully realise Finance Managers vision.
Week 21 | FBP 2.0 | Individual Work | Finance | 2 | 1.75
Week 22 | Tender Presentation | Meeting | Marketing | 1.5 | 1.25
Week 22 | Finance Report Meeting with Financial Advisor | Meeting | Finance | 0.25 | 0.25
Week 23 | Progress with ImageViewerTest | Individual Work | Development Testing | 0.5 | 0.5
Week 23 | Progress with ImageViewer | Individual Work | Development - Client Software | 0.5 | 0.5
Week 23 | Further tweaks to ImageViewerTest | Individual Work | Development Testing | 0.5 | 0.5
Week 23 | Further tweaks to ImageViewer | Individual Work | Development - Client Software | 0.25 | 0.25
Week 24 | Updated ImageViewerTest | Individual Work | Development Testing | 0.75 | 0.75
Week 24 | Updated ImageViewer | Individual Work | Development - Client Software | 0.25 | 0.25
Week 31 | Accountant QA Manual Role Review | Individual Work | Documentation | 0.5 | 0.75
Week 33 | Timesheet tweaks | Individual Work | Finance | 0.25 | 0.25
Week 33 | Implemented constructors for graphics and media elements in Presentation | Individual Work | Development - Client Software | 1 | 3 | Had some issues with navigating the xml file, as well as git issues related to merging branches etc. Initially had to spend a lot of time getting used to the current status of the code as it had been a while since I last did any development, and there were some missing files that hadn't been merged into the branch which took up more time to sort out.
Week 35 | Refactored some UIElements | Individual Work | Development - Client Software | 2 | 2 | Took a long time to figure out the the functionality of some of the code due to unclearvariable/method naming, and a lack of comments.
Week 35 | Finished efactoring CircularButton and SidebarScene | Individual Work | Development - Client Software | 2.5 | 2.5
Week 36 | Refactoring and extending functionality of LoginScene | Individual Work | Development - Client Software | 2 | 2 | Had to resolve a lot of merge conflicts when merging Paul's code into my branch. Had to spend time understanding Paul's code and the function of tokens.
Week 36 | LoginScene | Individual Work | Development - Client Software | 3 | 3 | Spent most of the time getting the branch to work rather than actually coding. Infruriating.
Week 36 | Group photos | Meeting | Marketing | 1 | 1
Week 36 | LoginScene | Individual Work | Development - Client Software | 3 | 3
Week 36 | Lost lots of changes when merging and had to recover with Jon and spent a while getting the server to work with Paul | Meeting | Development - Client Software | 0 | 3.5
Week 36 | Users can now successfully login | Individual Work | Development - Client Software | 1.5 | 1.5
Week 36 | Create Account successfully implemented | Individual Work | Development - Client Software | 4 | 4
Week 36 | LoginScene tweaks | Individual Work | Development - Client Software | 0.5 | 0.5

## Will
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | Fixed bug in VideoPlayer. Should no longer need to be configured per user. | Individual Work | Development - Client Software | 0.5 | 0.5
Week 22 | Critical Path diagram first draft | Individual Work | Integration and Testing | 3 | 2 | Missing info; could not complete to the standard I wished. Will have to rework.
Week 22 | Integration & Test Plan Meeting | Meeting | Integration and Testing | 1 | 1
Week 23 | Updated videoplayer to new methods, requested pull | Individual Work | Development - Client Software | 1 | 1
Week 23 | SidebarScene updates; should now have all critical functionality | Individual Work | Development - Client Software | 2 | 2 | Will still need some refining before merging. Hit a bit of a wall.
Week 23 | Attempt to test presentation integrated into sidebar scene | Individual Work | Development - Client Software | 2 | 2 | Very little luck. Presentations do not appear visible. Will need to talk to fraiser.
Week 23 | Fix divide by 0 in Presentation | Individual Work | Development - Client Software | 0 | 0.25 | Unplanned; happend while investigating above
Week 23 | Test and integration plan suggestions | Individual Work | Integration and Testing | 0.75 | 0.75
Week 24 | Try to test fraser's code for handling what happens when VLC is not installed | Individual Work | Development Testing | 0.75 | 1.75 | Managed to break every other test in the process. Still havent figured out what the problem is
Week 24 | Modified sidebarScene to use gridbaglayout. Actually works now. | Individual Work | Development - Client Software | 2 | 2
Week 24 | Modify tests to match sidebarScenes new layout | Individual Work | Development Testing | 0.25 | 0.25
Week 24 | weekly meeting, mostly worked on helping people with their tests | Meeting | Development Testing | 2 | 2
Week 25 | Test and integration plan meeting | Meeting | Integration and Testing | 1 | 1
Week 25 | Test and integration plan | Individual Work | Integration and Testing | 2 | 2
Week 25 | Working with Jon on sidebarscene. | Meeting | Development - Client Software | 0.75 | 0.75
Week 25 | Test and integration plan, section S2 unit tests | Individual Work | Integration and Testing | 0.5 | 0.5
Week 30 | Meeting with Sophie about priorities going forward | Meeting | Marketing | 0.75 | 0.75
Week 31 | Processed survey data | Individual Work | Marketing | 2 | 2
Week 31 | Group meeting, mainly spent looking at tests | Meeting | Integration and Testing | 1.5 | 1.5
Week 33 | Generated test reports | Individual Work | Integration and Testing | 0.25 | 0.75 | Took far longer than expected as most branches wouldn't generate proper reports
Week 33 | Weekly meeting, mostly discussed how to test Sophie's code | Meeting | Integration and Testing | 1 | 1.25
Week 33 | General tidyup on the UIElements branch ahead of unit testing | Individual Work | Development - Client Software | 2 | 2
Week 33 | Meeting with sophie and sri about UIElements branch | Meeting | Development - Client Software | 1.75 | 1.75
Week 35 | Meeting with group | Meeting | Development - Client Software | 3 | 1 | Left early; was halfway unconcious after exam
Week 35 | Generated test reports | Individual Work | Integration and Testing | 0.5 | 0.5 | Can now generate reports properly, but most branches are stale.
Week 35 | Saturday group work | Meeting | Development - Client Software | 3 | 2 | Train was cancelled so arrived at meeting late. Spent most of the meeting discussing the refactor. Did some code-cleanup.
Week 36 | CircularButton Test | Individual Work | Development Testing | 1 | 2 | AssertJ swing can really be un-cooperative sometimes. Spent ages trying to figure out why blue != blue. Suspect it is something to do with the alpha channel. Minor enough that I just removed the offending test.
Week 37 | 1st final pres rehersal | Meeting | Marketing | 1 | 1
Week 37 | 3rd final pres rehersal | Meeting | Marketing | 1.5 | 1.5
Week 37 | Presentation XML parser testing | Individual Work | Development Testing | 3 | 3 | For the amount of time that I spent on this, not a lot was accomplished. This part of the class is awkward to test.

## Srikanth
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | HTML Tour Setup | Individual Work | Documentation | 3 | 4 | Setup and basic design in Jekyll with Ruby
Week 22 | HTML Tour Setup | Individual Work | Documentation | 3 | 3 | Jekyll Theme changes and test posts
Week 22 | Tender Presentation | Meeting | Marketing | 1 | 1
Week 25 | HTML Tour Diagram | Individual Work | Documentation | 2 | 3 | Basic First Iteration design of HTML Tour
Week 26 | LoginScene updates | Individual Work | Development - Client Software | 3 | 5 | Commenting code
Week 27
Week 30 | HTML Tour GitHub Setup | Individual Work | Documentation | 2 | 2 | Using GitHub Pages to host the website
Week 31 | HTML Tour Second Draft | Individual Work | Documentation | 3 | 4 | Basic mockup of the HTML Tour from diagram
Week 31 | User Manual Research and Creation | Individual Work | Documentation | 2 | 3 | Researching good aesthetic designs, setup User manual in LaTeX
Week 32 | User Manual Title Page | Individual Work | Documentation | 3 | 3 | Designing User manual title page in LaTeX
Week 32 | VCS Repository Check-up/Re-arrangement | Individual Work | Development - Client Software | 1 | 2 | Code Rebase to main due to issues with the current structure
Week 33 | Merge main into mainScene branch | Individual Work | Development - Client Software | 1 | 1 | Merge
Week 33 | Setting up local development environement for comparisions | Individual Work | Development - Client Software | 2 | 2
Week 33 | Main group meeting and User Manual work | Meeting | Documentation | 1 | 1.5 | General Meeting to discuss User Manual
Week 35 | Refactoring sideBarUIElements pt 1 (at meeting) | Meeting | Development - Client Software | 3 | 3 | Removing Un-neccessary code, adding comments
Week 35 | Refactoring sideBarUIElements pt 2 (at meeting) | Meeting | Development - Client Software | 3 | 3 | Removing Un-neccessary code, adding comments
Week 35 | User Manual Work | Individual Work | Documentation | 0.5 | 1 | Managing access to User Manual
Week 35 | Git checkup | Individual Work | Development - Client Software | 1 | 1.5 | Branching from UIElements, tracking different new branches mapTheme, UIRefractor
Week 36 | New GUI redesign test | Individual Work | Development - Client Software | 1.5 | 3 | Testing new designs with Netbeans GUI designer, scrapped due to time constraints
Week 36 | Rebase changes from main into UIElements | Individual Work | Development - Client Software | 0.5 | 1
Week 36 | Merge main into UIElementsPresentationFix | Individual Work | Development - Client Software | 0.5 | 1
Week 36 | Updating sidebarScene to take new Presentations | Individual Work | Development - Client Software | 3 | 6 | The Presentation is now loaded into the sidebar, PresentationPanel has been completely removed. Needs further testing to prove functionality. Bugs where the content doesn't load on first click. Need to re-evaluate listeners.
Week 36 | Testing other various fixes | Individual Work | Development - Client Software | 2 | 4 | Improving window resizing functions, drafting better mainScene for this design, refactoring and recommenting code to improve readability
Week 36 | HelpScene PDF Loader first version | Individual Work | Development - Client Software | 4 | 6 | Issue with correct width of the pdf view took a long time to fix, classic one line fix.
Week 37 | HelpScene upgrade UI to app UI spec, fix bugs | Individual Work | Development - Client Software | 3 | 5 | Fixed the bug where the pdf would loop forever, now inside a JPanel for easier loading, boxLayout fixes the layout issues.

## Sophie
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | Demo video for tender pres: code + video | Individual Work | Marketing | 3.5 | 3.5
Week 21 | Marketing and design road map | Individual Work | Marketing | 1 | 1
Week 21 | Software: finishing upload scene visually | Individual Work | Development - Client Software | 2 | 2
Week 21 | Tender presentation: demo video reworked, researched+ wrote marketting strategies, made roadmaps | Individual Work | Marketing | 3 | 3
Week 22 | Tender Pres | Meeting | Marketing | 1 | 1
Week 23 | Text Contract: Code (rough) | Individual Work | Contracts | 4 | 4
Week 23 | Text Contract: Code (finished) | Meeting | Contracts | 2 | 2
Week 23 | Text Contract: Tests (rough) | Individual Work | Contracts | 1 | 1
Week 23 | Reworked surveys | Individual Work | Marketing | 0.5 | 0.5 | Added some questions to get some design stats to support our design choices in final pres.
Week 23 | Text contract: Tests (nearly finished) | Individual Work | Contracts | 2 | 2
Week 24 | Text contract testing | Meeting | Contracts | 2 | 2 | Needed help with some costructor fields and the timeOnScreen test
Week 24 | Login screen visual improvements | Individual Work | Development - Client Software | 2 | 2 | Worked on the graphics by adding some annonmous classes and working with their paint methods within loginScene and the same with the loginScene panel itself to get look and feel roughly similiar to mockups (this will need a tiny bit more work to clean up look and feel of buttons and to add dimension to everything)
Week 25 | Marketting surveys sent | Individual Work | Marketing | 0.5 | 0.5 | Email sent to general office including a section that will be sent to 1st year students containing the google survey form
Week 26 | Side bar scene coding | Individual Work | Development - Client Software | 4 | 4 | Took out the annonymous classes and made standard classes for custom components. 'Header' holds the search bar object and all the sidebar interaction buttons. Customised the scroll bar UI. Added animation to the search bar and custom back panel (both close and open dynamically, taking a long time variable to adjust speed). Customised the buttoms (search, minimise, maximise). I have added a placeholder 'filterMenu' button to the header that will be replaced by a drop down menu for user to filter search. Changed the search text field so once search button is pressed, text turns first letter to upper case: 'sweng' becomes 'Sweng' and if sidebar is closed- it will then open. Created a 'presentationPanel' class which resizes slides to fill viewport in scroll pane, class also contains the overlay which i have equipped to become visible when you hover on the post. I added a placeholder description in the centre of the overlay but this will be replaced with the .getDescription from the post and will also display: buttons to go back and forth in the presentation, bubble track thing ( < o o o o > ), report button, author, date and activity status ( TICK ) / ( CROSS ) (depending on whethet event is going on). All components take two colours for setBackground. All components are stacked according to their z order. Note: the scroll bar is seperated from the scroll pane, (VERTICAL_SCROLLBAR_ VISIBLE_NEVER) .getVerticalScrollBar() and then placed onto the sideBar so as to go over the top of the posts.
Week 26 | UploadScene coding | Individual Work | Development - Client Software | 5 | 5 | Added some functionality: presentationBox- now contains 'layer' objects which hold a list of bufferedIMages, it also has methods to paint/ erase and go back. The way this works is everytime a graphic is added to the presentation, an image is created an added to the layer's imageList. When the presentation is painted, it goes through the layerlist and paints it's current position in it's imageList. Going back or forward just change a layers' position in it's imagelist. Erasing takes the current image of a layer and removes pixels from where mouse is dragged. Note: it doesn't just paint those to white/ background color, this is so graphics can be removed from layers without removing from other layers. The annonmous layer class also holds a string name, this and the list of layers will be what constructs the graphicsBoxList. I have also added an eraser button and a go forward button. Another thing I've added to the presentationbox is paintMode and eraserMode, this tells the mouseListeners what is added to the presentation image. These modes will also include an addShapesMode, addTextMode ect ect.
Week 29 | UploadScene coding | Individual Work | Development - Client Software | 7 | 7 | Done a huge redesign,changing the hierarchy completely, graphics box is the central control of pres elements on the slide. Graphics Box shows elements and can create a new graphics layer or delete a layer. A layer is selected by clicking it on, when a layer is selected tool bar is told and if the layer is a graphic specific layer then a mouse listener is added to the slide to add a graphics element. Graphic element contains an array of images (basically all the code that was previuously in the presentationBox). I've added a getter to the presElement to get a string of its type, i.e "TEXT" "GRAPHIC" "IMAGE" ect. so edditing presElements is easier. I've created the mediaBox, where when you initially click on it, it opens a filechooser than you can select a file. At the moment it only accepts ".jpeg" and ".png" but this will be changed. - I had to create a new ImageElement class that doesn't have the url in the constructor. when an image is selected, an icon version of it appears in the media box, if you then click on the icon it then becomes the cursor and then if you click on the slide you want to add it to, the image origanlly selected is added to the slide as an Image element. The move button has also been slightly implemented, if a layer is selected and you click on the move icon, a 'move object' is diplayed around the presElement with arrow buttons in each corner to drag the to resize it. - this isnt fully finished but will finish after the whole scene has been finshed. I have also created three different layout types for the slide which are specified when the slide is created. (landscape, portrait, square). Have also added a background to the tabPane, idk i think it makes it look a bit more prefessional. Side note: im coding this so each 'layer' is a pres element.
Week 29 | UploadScene coding | Individual Work | Development - Client Software | 6 | 6 | Tag box implemented,Properties box implemented to display current selected element position, size and duration which you can change (its buggy so needs more work), shape and text buttons have been implemented to add a text element and a circle element to the slude(for now, will add a popup to choose shape). I'm trying to speed through this all as quick as i can but with this scene being so large its becoming quite buggy in places- may need some extra help going into next term.
Week 30 | UploadScene coding | Individual Work | Development - Client Software | 4 | 4 | Description box added and theres now some getters to retrieve the description input from the user and a list of tags from the tagsBox when user confirms their finsihed. Have also implemented a progress bar to the bottom of the tabPane with a play/ pause and audioOn/Off button, the bar takes the maximum duration of elements on the current slide and when you press play the bar inccreases to a maximum in that time.
Week 30 | Leadership meeting | Meeting | Marketing | 1 | 1
Week 30 | Market meeting prep | Individual Work | Marketing | 0.25 | 0.25 | Put together some information and created some tasks for the following week
Week 30 | MainScene coding | Individual Work | Development - Client Software | 1 | 1 | Put scenes together in mainScene branch for design analysis. theres an error with a colour in uploadscene will fix tomorrow
Week 30 | MainScene coding | Individual Work | Development - Client Software | 0.25 | 0.25 | ^ fixed
Week 30 | Design Team meeting | Meeting | Marketing | 0.5 | 0.5 | Minutes are in the doc team folder.
Week 31 | UploadScene coding | Individual Work | Development - Client Software | 2 | 2 | So the tabbedPane is the central class for instatiating slides, the components that need information about current visible slides are passed in through the constructor (elementsPanel + timeBar) or are instatiated within the class (tool bar+ mediaPanel). Added a bunch of comments so should be fairly easy to understand whats happeneing. I havn't finished this as theres an error whilst creating slides. Not entirely sure why they arent appearing in the tabPane, have tried everything i can think of to resolve it. without the slide appearing i cant make sure elements are being created right within elementsPanel or showing up correctly on elementsPropertiesPanel- will need some help to resolve this please I have refactored so the ElementsPanel is the central class to store information about the presElements on the current visible slide, elementsProperties is passed in through the constructor
Week 33 | Scene design cohesian | Individual Work | Marketing | 0.5 | 0.5 | Made an interface which all scenes now use which has the colours and curvatureRadius in
Week 33 | UploadScene coding | Individual Work | Development - Client Software | 1 | 1 | Added comments for Fraser, made a uml type diagram and gridBounds+ insets diagram
Week 33 | UploadScene coding | Individual Work | Development - Client Software | 0.5 | 0.5 | Eraser button all working. Position of elements are all off but this should be all good to start intergration with server now
Week 34 | UploadScene coding/ main scene coding | Individual Work | Development - Client Software | 4 | 4 | Moving object is implemented, when an element is selected in the elements panel and the move tool is selected you can drag to change the elements position and you can drag any of the four corners to change it's size. The text input has been started, when a text element is selected and the move tool is selected you can click on the text element and a text field will be visible (so users to input text) - this hasnt been finished. Main scene components all resize with frame now and I fixed an issue in upload scene when it was resizing slides.
Week 35 | Final Pres | Individual Work | Marketing | 4 | 4 | Researched sales presentations, good examples and good structures. Created a structure and created a basis for the slides. Started designing slides. Started writing speech. Created stats to suit slide colour scheme.
Week 36 | Final Pres | Individual Work | Marketing | 2 | 2 | More work on the slides. Worked on layout and design of slides.
Week 36 | Final Pres | Meeting | Marketing | 3 | 3 | More work on the slides and the speech, speech is basically finished, missing demo commetry and introduction. Slides are basically finished, finishing touches on slides.
Week 36 | Final Pres | Individual Work | Marketing | 2 | 2 | Animation implimentation, reworked structure to include more graphs, created a comparisons chart of competitor companys and researched the event discovery and hosting platform market and found growth stats and worth.
Week 36 | final Pres | Individual Work | Marketing | 2 | 2 | Speech work, rewrote value propersition part, included aan in depth analysis of our marketting/business plan- this may have to be modified to include finational projection
Week 36 | final Pres | Meeting | Marketing | 0.5 | 0.5 | Meeting with Matteo about pres structure, the structure is now changed and the diagram of the structure is in the marketting chat
Week 36 | final Pres | Individual Work | Marketing | 2 | 2 | Did some research into good design philosophy, have written the speech for this section of the presentation
Week 36 | Accesibility coding + XML Output from Upload scene | Individual Work | Development - Client Software | 2 | 2 | The XML Output for the upload scene may not get used but i thought it was worth documenting. When you confirm making a post, you get presentated with the file explorer to save the presentation in XML format. Wrote code to create a document, creates elements based on the pres elements and adds the atributes, then transforms into an xml file. I have also seperately added a key listener to the main scene because we dont have any accesible features in the code as it it and it's good for our design philosophy. The key listener means users can operate the application with the keyboard instead of using the mouse. Controls are: SHIFT + C and SHIFT + O to open and close the side bar scene, and SHIFT + S and SHIFT + BACKSPACE to request and lose focus on the searchbar respectively.
Week 36 | Final Pres | Individual Work | Marketing | 3 | 3 | Started redesigning new slides and got basically half done, not a fan of the current theme, finished writing my speech
Week 36 | Final Pres | Meeting | Marketing | 1 | 1 | 1st rehearsal of final pres
Week 36 | Final Pres | Individual Work | Marketing | 3 | 3 | Re-did the theme for the slides because i didnt like the old one, Finished my speech, created graphs for the projected finance section,added animations to slides, sorted out glitches in transitions.
Week 36 | Final Pres | Meeting | Marketing | 2 | 2 | 2nd Rehearsal for final pres
Week 37 | Final Pres | Meeting | Marketing | 1.5 | 1.5 | 3rd Rehearsal

## Oliver
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | Tender Presentation preperation | Individual Work | Marketing | 2 | 5 | Had difficultly describing the diagrams in a professional manor because they werent made by me
Week 21 | AudioPlayer Code | Individual Work | Development - Client Software | 1 | 1
Week 22 | Tender Presentation | Meeting | Marketing | 0.5 | 0.5
Week 22 | Audio player coding | Individual Work | Development - Client Software | 2 | 2
Week 24 | Audio Player Coding | Individual Work | Development - Client Software | 5 | 5 | Had trouble adapting standard methods into code that could work with our Architecture.
Week 24 | Audio player | Individual Work | Development - Client Software | 2 | 2
Week 30 | Writing email for surveys | Individual Work | Marketing | 1 | 0.5
Week 31 | HTML tour design | Individual Work | Marketing | 3 | 4 | ended up researching into the design longer than anticipated
Week 31 | AudioPlayer changes and sending pull request to merge | Individual Work | Marketing | 1 | 1.5 | extra changes to make
Week 31 | Team meeting | Meeting | Marketing | 2 | 2
Week 33 | Leadership meeting | Meeting | Finance | 1.5 | 1.5
Week 34 | General meeting | Meeting | Development - Client Software | 1 | 2.5
Week 35 | General meeting | Meeting | Marketing | 2 | 2
Week 35 | Group Photography | Individual Work | Marketing | 1 | 1
Week 35 | General meeting | Meeting | Marketing | 2 | 3 | Task was not descibed for what was required, lots of changes kept being made

## Matteo
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | New timesheet Concept Creation | Individual Work | Finance | 0.5 | 0.5
Week 21 | Intergroup Contracts Review and Editing | Individual Work | Documentation | 0.5 | 0.5
Week 21 | Tender Presentation Speech Intro and Outro | Individual Work | Marketing | 0.25 | 0.25
Week 21 | Tender Presentation Speech and Slide tweaks | Individual Work | Marketing | 2 | 4 | Late information from lecturer alluded to requirements not currently met
Week 22 | Tender Presentation Finalisation | Individual Work | Marketing | 2 | 2
Week 22 | Tender Presentation Practise run | Meeting | Marketing | 1 | 1
Week 22 | Tender Presentation | Meeting | Marketing | 0.5 | 0.5
Week 22 | Financial Report 1 meeting with business mentor | Meeting | Finance | 0.25 | 0.25
Week 22 | FInancial Business plan 2.0 final tweaks | Individual Work | Finance | 0.5 | 1 | Difficulty applying compound interest formula to a period of less than a calendar year
Week 22 | Financial Report 1 | Individual Work | Finance | 1 | 1
Week 24 | Financial Report 2 | Individual Work | Finance | 1 | 3 | Some Team members weren't able to meet the deadline for logging hours + I was hungover
Week 30 | Design Team Meeting | Meeting | Marketing | 0.5 | 0.5 | Contents in Meeting Minutes folder
Week 30 | Finance team briefing | Meeting | Finance | 0.25 | 0.25
Week 31 | Review of Finance Manager Role for QA Manual Update | Individual Work | Documentation | 2 | 2
Week 31 | Catch-up meeting with PM | Meeting | Finance | 1 | 0.5
Week 31 | Create Beta Testing Personel availability Questionnaire | Individual Work | Marketing | 0.5 | 0.5
Week 32 | Meeting with Tony Ward to discuss some financial aspects and clarify some project doubts | Meeting | Finance | 0.5 | 0.5
Week 32 | Modification to first iteration of YUSU LOI | Individual Work | Documentation | 1 | 0.75
Week 32 | Financial Report 3 | Individual Work | Finance | 1 | 3 | Longest report yet due to biggest timespan
Week 33 | Final Financial Plan Meeting | Meeting | Finance | 2 | 1.5
Week 33 | Pricing scheme prep | Individual Work | Finance | 1.5 | 1.5
Week 34 | Leadership meeting to discuss finances | Meeting | Finance | 1.5 | 1.5
Week 35 | Discussed server hosting overheads and pricing strategies for finance plans | Meeting | Finance | 0.5 | 0.5
Week 35 | Discussed what needs to go in the HTML tour, a few design choices. | Meeting | Documentation | 1 | 1
Week 35 | Discussed client app progress and mitigating bottlenecks during the development process | Meeting | Development - Client Software | 1 | 1
Week 35 | Wrote Final Finance Report | Individual Work | Finance | 15 | 12 | I am quicker at writing than anticipated.
Week 35 | Wrote text fields for HTML Tour | Individual Work | Documentation | 1 | 1
Week 36 | Wrote text fields for HTML Tour | Individual Work | Documentation | 1 | 1
Week 36 | Wrote speech for Sales Presentation | Individual Work | Documentation | 2 | 2
Week 36 | headshots | Meeting | Documentation | 1 | 1
Week 36 | Wrote speech for Sales Presentation | Individual Work | Marketing | 3 | 3
Week 36 | meeting to finalise pres structure | Individual Work | Marketing | 1 | 1
Week 36 | sales pres speech update | Individual Work | Marketing | 2 | 2
Week 36 | sales pres practise | Meeting | Marketing | 2 | 2
Week 36 | Sales pres practise | Meeting | Marketing | 2 | 4 | I wanted the delivery to feel natural, so I abandoned the written speech and improvised the speech. This required a great deal of practise to get it sufficiently succint and well worded.
Week 36 | final presentation last tweaks | Individual Work | Marketing | 1 | 1
Week 37 | Pre sales pitch practise | Meeting | Marketing | 1.5 | 1.5
Week 37 | sales pitch | Meeting | Marketing | 0.75 | 0.75
Week 37 | Update QA Manual sections for FM and accountant | Individual Work | Documentation | 1 | 1
Week 37 | GDrive clean-up | Individual Work | Documentation | 0.5 | 0.5

## Paul
ecl | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | Creation of TDD Diagram for Tender Presentation | Individual Work | Documentation | 2.5 | 1.5 | Went easier than I expected - found simple software for creating the diagram.
Week 21 | Test & Integration Plan Research / Initial Writing | Individual Work | Integration and Testing | 1 | 1
Week 21 | Test & Integration Plan Research / Initial Writing | Individual Work | Integration and Testing | 1.5 | 1.5
Week 21 | Server Test Writing | Individual Work | Development - Server Software | 1.5 | 3 | Unexpected bugs found.
Week 22 | Server Test Writing | Individual Work | Development - Server Software | 1 | 1
Week 22 | Test & Integration Plan Meeting | Meeting | Integration and Testing | 1 | 1
Week 22 | Tender Presentation | Meeting | Marketing | 1 | 1
Week 23 | Test & Integration Plan Writing | Individual Work | Documentation | 2 | 2
Week 23 | Test & Integration Plan Writing | Individual Work | Documentation | 2 | 2
Week 23 | Server Test Writing | Individual Work | Integration and Testing | 1.5 | 1.5
Week 23 | Server Test Writing | Individual Work | Integration and Testing | 0.5 | 0.5
Week 23 | Server Test Writing | Individual Work | Integration and Testing | 3 | 3
Week 23 | Test & Integration Plan Planning | Individual Work | Integration and Testing | 0.5 | 0.5
Week 23 | Server Test Writing | Individual Work | Integration and Testing | 1.5 | 1.5
Week 23 | Test & Integration Plan Writing | Individual Work | Documentation | 0.5 | 0.5
Week 23 | Test & Integration Plan Writing | Individual Work | Documentation | 2 | 2
Week 24 | Test & Integration Plan Writing | Individual Work | Documentation | 1 | 1
Week 24 | Server Test Writing | Individual Work | Integration and Testing | 1 | 1
Week 25 | T&I Plan Meeting | Meeting | Documentation | 0.75 | 0.75
Week 25 | Server Test Writing | Individual Work | Development Testing | 1 | 1.5 | Unexpected issues with docker, resolved now
Week 25 | T&I Plan Writing | Individual Work | Documentation | 3 | 3
Week 25 | T&I Plan Writing | Individual Work | Documentation | 2 | 2
Week 25 | Server Test Writing | Individual Work | Development Testing | 1 | 1 | T
Week 29 | Server Test Writing | Individual Work | Development Testing | 2 | 3 | Learning how to do the endpoints tests properly took a little longer than expected due to my unfamiliarty with HTTP, but now that's done it should be straightforward and quick to test the rest of the endpoints.
Week 29 | Server Test Writing | Individual Work | Development Testing | 1 | 1.5 | Encountered some issues around testing with spring security, will need to be perform more research
Week 30 | Server Test Writing | Individual Work | Development Testing | 4 | 4
Week 30 | Leadership team synchronisation meeting | Meeting | Development - Server Software | 1 | 1.5
Week 31 | Server Test Writing | Individual Work | Development Testing | 4 | 4
Week 31 | Discussed Code Coverage Solutions | Meeting | Development Testing | 1 | 1
Week 31 | Wrote Hashtag Tests | Individual Work | Development Testing | 3 | 3
Week 32 | QA Manual Role Review Writing | Individual Work | Documentation | 0.5 | 0.5 | More work required, want to provide more depth than I intially anticipated.
Week 32 | Researching Acceptance Tests | Individual Work | Development Testing | 0.5 | 0.5
Week 33 | Client & Server Integration Development | Individual Work | Development - Client Software | 4 | 5 | Unexpected issues with getting request into the right format
Week 35 | Client & Server Integration Development | Individual Work | Development - Client Software | 4 | 4
Week 35 | Client & Server Integration Development & Testing | Individual Work | Development - Client Software | 4 | 4
Week 35 | Client & Server Integration Development at Group Session | Individual Work | Development - Client Software | 3 | 3
Week 35 | Client & Server Integration Development & Testing | Individual Work | Development - Client Software | 3 | 3
Week 36 | Client & Server Integration Development & Testing | Individual Work | Development - Client Software | 4 | 4
Week 36 | Client & Server Integration Development & Testing | Individual Work | Development - Client Software | 2 | 5 | Had to hunt down a frustrating bug on the server - turned out to be a too low constraint on the post XML content length.
Week 36 | Client & Server Integration Development & Testing | Individual Work | Development - Client Software | 3 | 3
Week 36 | Wrote guide on setting on server software locally | Individual Work | Development - Client Software | 0.75 | 0.75
Week 37 | Final push on the client server integration, XML writing, testing of various elements for the demonstration | Individual Work | Development - Client Software | 5 | 8 | Refactoring had to be done to get MacOS to display videos correctly, as well as other misc bugs taking up more time than expected.
Week 37 | Sales Presentation + Prep | Meeting | Marketing | 2 | 2
Week 37 | Manual GUI Testing | Individual Work | Development Testing | 8 | 5 | Expected this to be a full day job, but was a bit easier than I expected.
Week 37 | Acceptance Testing & Report | Individual Work | Documentation | 3 | 3
Week 37 | QA Manual Role Review Writing | Individual Work | Documentation | 0.25 | 0.25
Week 37

## Sidharth
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | Intergroup Contracts: Putting together acceptance criteria and finance sections | Individual Work | Documentation | 1.5 | 2 | I had to rewrite and reformat a lot of the acceptance criteria content provided by Fraser
Week 21 | Intergroup Contracts: finalising and exporting draft for initial exchange | Individual Work | Documentation | 0.5 | 0.5
Week 21 | Tender Presentation: created diagram explaining server architecture | Individual Work | Marketing | 1 | 0.75
Week 21 | Intergroup meeting regarding contracls | Meeting | Documentation | 0.5 | 0.5
Week 21 | Intergroup Contracts: updated clause 1.3 and reviewed acceptance criteria updates | Individual Work | Documentation | 0.25 | 0.25
Week 21 | Tender Presentation: catch-up meeting with the team | Meeting | Marketing | 0.5 | 0.5
Week 21 | Server code review and added toString to Map entity | Individual Work | Development - Server Software | 0.5 | 0.5
Week 21 | Server code: implemented Role and Post models to the User model | Individual Work | Development - Server Software | 0.5 | 0.5
Week 21 | Server code: Updated User unit test to incorporate Post and Role inclusion | Individual Work | Development - Server Software | 0.5 | 0.5
Week 21 | Server code: Researched and reworked Media API plan to include filetype support | Individual Work | Development - Server Software | 0.5 | 1 | I initially thought adding a filetype extension would suffice, but it turns out APIs use something called MIME Type, I had to research and implement it in the plan
Week 22 | Tender Presentation: Rehearsals | Meeting | Marketing | 1 | 0.75
Week 22 | Tender presentation and group catch-up | Meeting | Marketing | 0.5 | 0.5
Week 22 | Server code: fixing failing tests in the UserRepository | Individual Work | Development - Server Software | 0.5 | 1 | A few issues popped up due to the "ToMany" relationship that User has with Role and Post
Week 22 | Server code: updated tests for stability | Individual Work | Development - Server Software | 1 | 1
Week 22 | Server code: A default and built-in Spring Boot test was failing, I had to fix this | Individual Work | Development - Client Software | 1 | 1
Week 23 | Server code: reviewing and merging User Role Post relationship branch | Individual Work | Development - Server Software | 0.25 | 0.25
Week 23 | Created the User Service layer | Individual Work | Development - Server Software | 1 | 1.5 | Encountered a few issues with Optional data in Spring
Week 23 | Created the Role Service layer | Individual Work | Development - Server Software | 1 | 1
Week 23 | Created the Post Service layer | Individual Work | Development - Server Software | 1 | 1
Week 23 | Created the Media Service layer | Individual Work | Development - Server Software | 1 | 1
Week 23 | Created the Map Service layer | Individual Work | Development - Server Software | 1 | 1
Week 23 | Fixing an exception in Service Layer tests | Individual Work | Development - Server Software | 0.5 | 0.5
Week 23 | Updating Media Service to handle filesystem saving and deletion | Individual Work | Development - Server Software | 1.5 | 1.5
Week 24 | Merged service branches and verified all tests pass on main branch after merge | Individual Work | Development - Server Software | 0.5 | 0.25
Week 24 | Added JWT auth filters and configurations | Individual Work | Development - Server Software | 1 | 1.5 | Spent longer trying to add auth permission rules for API endpoints so I will save time when implementing the endpoints.
Week 24 | Updated map service layer to incorporate filesystem storage | Individual Work | Development - Server Software | 0.5 | 1 | Had issues with the mocking library for testing to ensure TDD
Week 24 | Integration: fixed a functionality conflict with another | Individual Work | Development - Server Software | 0.5 | 1 | There was an issue with the CommandLineRunner method which is designed to run when the app is started to initialise a default Admin user. It was causing conflicts with other classes and thus failing tests. It was a difficult one to debug.
Week 24 | Documentation synchronisation - catching up with what needs to be done and what's been done with individual people | Meeting | Documentation | 0.5 | 0.5
Week 24 | Reviewing, merging, and fixing failing integration tests | Individual Work | Development - Server Software | 1 | 1
Week 24 | Reviewing contracted work | Meeting | Contracts | 0.5 | 0.5
Week 25 | Reviewed feature/jwt-auth-configuration branch, refactored and merged to main | Individual Work | Development - Server Software | 0.25 | 0.25
Week 25 | Had issues with refresh tokens, jwt logic had to be refactored | Individual Work | Development - Server Software | 0.25 | 0.25
Week 25 | JWT logic couldn’t access environment variables, code had to be refactored to fix | Individual Work | Development - Server Software | 1 | 1
Week 25 | Map entity POST endpoint controller | Individual Work | Development - Server Software | 1 | 1
Week 25 | createMap service implementation had to be refactored to generate name and ID before save | Individual Work | Development - Server Software | 0.25 | 0.25
Week 25 | Map entity GET endpoint controllers | Individual Work | Development - Server Software | 1.5 | 1.5
Week 25 | Reviewing T&I Plan | Individual Work | Integration and Testing | 0.25 | 0.25
Week 25 | Preparing for 1st iteration demo | Individual Work | Development - Server Software | 0.25 | 0.25
Week 25 | Refactoring tests and writing DELETE map endpoint | Individual Work | Development - Server Software | 0.5 | 0.5
Week 25 | Knowledgebase sharing with Paul - explaining controllers using my spikes and debugging some issues | Individual Work | Development - Server Software | 0.5 | 0.5
Week 25 | Client-Server interaction section of the Testing & Integration Plan | Individual Work | Integration and Testing | 1 | 0.75
Week 25 | Preparing server software for the 1st iteration demo | Individual Work | Development - Server Software | 0.25 | 0.5 | Had an unexpected issue with Docker, I never had this issue before when running and this caused the database to go offline
Week 25 | 1st Iteration demo meeting with Tony | Meeting | Development - Server Software | 1 | 0.5
Week 25 | Preparing and sending weekly updates | Individual Work | Documentation | 0 | 0.25 | Preparing and sending these updates usually take up less time than the limit for the timesheet (15 mins), however this one took longer as it was quite a busy week.
Week 29 | Made fixes to tests and refactored code to comply with the tests | Individual Work | Development - Server Software | 1 | 2.5 | Paul spotted some compliance issues that my code had with the tests, I had to fix these. I found some issues that the tests had especially with mocking files for the maps, the tests was instantiating a map model but didn't create the files, a bit of a pain to sort this out as I had to find a way to create a temporary file in the tests which are destroyed after the tests complete.
Week 29 | Media endpoints | Individual Work | Development - Server Software | 2 | 1 | Creating the post/get/delete HTTP took less time than expected as most of the logic was very similar to the Map entity endpoints.
Week 29 | User endpoints | Individual Work | Development - Server Software | 2 | 2 | Could've taken less time, however, I had to spend longer to consider the security aspects of this endpoint
Week 29 | Post endpoints | Individual Work | Development - Server Software | 3 | 3 | Again, should've taken less time but Spring Boot is complicated and sometimes requires sketchy work arounds to get niche logic to work
Week 30 | Leadership team synchronisation meeting | Meeting | Development - Server Software | 1 | 1.5 | Some discussions took longer than planned
Week 30 | Refactored get post endpoint for better error handling | Individual Work | Development - Server Software | 0.25 | 0.25
Week 30 | Created the first version of the server app documentation/api reference | Individual Work | Documentation | 2 | 6.5 | Who knew that documenting something you've already developed would take so long? I didn't.
Week 31 | Catch up meeting with Matteo | Meeting | Finance | 1 | 0.5
Week 31 | Discussion on the HTML tour and catching up in group session | Meeting | Documentation | 1 | 1
Week 31 | Implemented the Hashtag logic in server software in group session | Individual Work | Development - Server Software | 1 | 1 | I'm such an idiot I literally wrote plans on implementing this but forgot to implement it in the end. Luckily only took an hour as most of the logic was simply a copy and paste from the 'Role' logic.
Week 31 | QA Manual Role Review | Individual Work | Documentation | 1 | 0.5 | Reviewed the QA Manual description of my role to refine it
Week 31 | Refactored Hashtag logic to so the tests pass | Individual Work | Development - Server Software | 1 | 1 | Managed to refactor my code so all the tests pass, except one. I really can't figure out why that one test is failing, I've spoken to Paul hopefully he can figure out what's causing the issue
Week 31 | Merged all of the tested Hashtag logic to main and updated server documentation | Individual Work | Documentation | 0.5 | 0.5
Week 32 | Group session | Meeting | Development - Server Software | 1 | 1 | This was a routine weekly group session, only Sri, Jon and Sophie turned up :-{. I ended up adding some more comments to the server software code (non-test code) so it's easier for reviews.
Week 32 | Meeting with Tony Ward to discuss some financial aspects and clarify some project doubts | Meeting | Finance | 0.5 | 0.5
Week 32 | Researched what a letter of intent is and started drafting one that we can potentially propose to the YUSU president | Individual Work | Documentation | 1 | 1
Week 32 | Made a start on writing the html tour website | Individual Work | Documentation | 1 | 1
Week 33 | Group session - discussed HTML tour | Meeting | Documentation | 0.25 | 0.5 | This was a great group session which pretty much the whole group turning up, we've managed to form a plan of action for the HTML tour and the client-server integration. We'd made quite a few changes in the plan when compared to the FS, so we had to update the FS accordingly. The 1h group session lasted almost 2h.
Week 33 | Group session - discussed client-server integration plan of action | Meeting | Integration and Testing | 0.25 | 0.5 | Mentioned in the above entry
Week 33 | Group session - updated FS to reflect most recent plan | Meeting | Documentation | 0.25 | 0.5 | Mentioned in the above entry
Week 34 | Leadership meeting to discuss finances | Meeting | Finance | 1.5 | 1.5
Week 35 | Discussed server hosting overheads and pricing strategies for finance plans | Meeting | Finance | 0.5 | 0.5
Week 35 | Updated the YUSU Declaration of Interest document and gave it a thorough review | Meeting | Marketing | 1 | 1
Week 35 | Discussed what needs to go in the HTML tour, a few design choices and delegated tasks | Meeting | Documentation | 1 | 1
Week 35 | Discussed client app progress and mitigating bottlenecks during the development process | Meeting | Development - Client Software | 1 | 1
Week 35 | Sales pitch to Pierrick (YUSU president) | Individual Work | Marketing | 1 | 0.75 | Blocked an hour of my time for this but went much smoother and quicker than I though, Pierrick was quite interested in the product and was able to sign the declaration of interest document with a testimony in a little over 45 minutes.
Week 35 | Reviewed written content from Matteo for the HTML tour about page and translated it into HTML | Individual Work | Documentation | 1 | 2 | Had to think of ways design-wise to make a block of text look nice and more legible
Week 35 | HTML tour pricing page | Individual Work | Documentation | 1 | 1
Week 35 | Proofreading the final finance report | Individual Work | Documentation | 0.5 | 0.5
Week 35 | Catch up meeting with Sophie and marketing to discuss presentation | Meeting | Marketing | 0.5 | 0.5
Week 35 | HTML tour downloads page, sorting out GDrive and arranging documents | Meeting | Documentation | 1.5 | 1.5
Week 35 | Refactored software code to re-write location logic and updated server documentation | Individual Work | Development - Server Software | 1 | 1 | Integration testing found that it's easier to associate a location with a hashtag (event) instead of the post itself.
Week 35 | Refactoring and fixing broken logic in HTML tour code | Individual Work | Documentation | 0.25 | 1 | We use Jekyll to create dynamic content for the HTML tour which can then be compiled into static HTML files for submission. The static html files weren't linking together properly along with assets. I had to spend a lot of time fixing this.
Week 35 | Make everything dynamically adjustable in the HTML tour with YAML files, no need to modify HTML source code | Individual Work | Documentation | 1 | 2.5
Week 36 | HTML tour stuff | Individual Work | Documentation | 1.5 | 1.5
Week 36 | Proofreading and fixing some issues in the user manual | Individual Work | Documentation | 1 | 1
Week 36 | Updated HTML tour fonts, styling and formatting | Individual Work | Documentation | 1 | 1
Week 36 | Group photos and headshots | Meeting | Marketing | 1 | 1
Week 36 | Final presentation script | Individual Work | Marketing | 1 | 3 | There was a lot of rewriting which had to be done so that the text sounds like something I would say
Week 36 | Final presentation script refinements | Individual Work | Marketing | 1.5 | 1.5
Week 36 | Final presentation rehearsal | Meeting | Marketing | 2 | 2
Week 36 | HTML Tour updating fonts for readability and fixing typos | Individual Work | Documentation | 1 | 1 | I wanted to use the same font as the What's On: logo for all of the headings - I thought it looked better but people didn't like it so I had to find a replacement 😢
Week 36 | Server software documentation review | Individual Work | Documentation | 0.25 | 0.25 | Proof reading, updating the version control table and fixing the formatting for more consistency
Week 37 | Final presentation rehearsal and script updates | Meeting | Marketing | 3 | 3
Week 37 | Final presentation | Meeting | Marketing | 1 | 1
Week 37 | QA manual updates and proofreading | Individual Work | Documentation | 1 | 1
Week 37 | Made repos for the server spikes I carried out | Individual Work | Development - Server Software | 0.5 | 0.5 | I really should've done this before in advanced. However, as it was just me and Paul working on the server app, I decided it would be easier to make a set of research/planning documents and sitting with him one-to-one to share knowledge from the spikes. Doing it my way turned . out much easier as Paul didn't have to spend hours parsing through the spike sourcecodes and watching several hours of YouTube courses. The reason why I'm creating repos for this now and copy-pasting the code from my computer is because I noticed I talked about these spikes in my timesheet yet there was no physical evidence of them.
Week 37 | Functional Specification refinements and review | Individual Work | Documentation | 2 | 2
Week 37 | HTML tour integrated team portraits | Individual Work | Documentation | 0 | 0.25 | Ideally, should've taken 5 minutes to download the images, and stick on to the tour, but had a lot of issues with Github as it started to throw fits as the images were massive. Had to compress all of the portraits by converting to jpeg
Week 37 | HTML tour integrated group photo | Individual Work | Documentation | 0 | 0.5 | Again, ideally should've taken barely any time to carry this out. I was faced with an issue where the image was rendering in my local environment but when compiled, the images returned a 404. Took ages to debug but this was due to the fact that I was referencing the image as .jpg instead of .JPG. The uppercase file extension caused this.
Week 37 | HTML tour integrated features screenshots and created GIFs | Individual Work | Documentation | 0.25 | 1 | Had a lot of issues with image sizing, had to manually force the max image size in HTML. Had to source screenshots from various locations and had to create a GIF
Week 37 | QA Manual review | Individual Work | Documentation | 2 | 6 | Should've been a brief review, but not many people turned up to this group session so it was just myself and Jon working on this
Week 37 | FS Review | Individual Work | Documentation | 0.5 | 0.5
Week 37 | User Manual Review | Individual Work | Documentation | 1 | 1
Week 37 | Meeting minutes review | Individual Work | Documentation | 0.5 | 0.5
Week 37 | Structuring the HTML tour by curating documentation | Individual Work | Documentation | 1 | 4 | Took much longer as people didn't do what they we're told to do so Jon and I had to go through every document, curate and export 😢
Week 37 | Linking compiled documents to the HTML Tour | Individual Work | Documentation | 3 | 3

## Sarujan
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | Rough Logo Designs | Individual Work | Marketing | 2 | 3.5 | I had gone through a few drafts & scrapped some designs before finalising a base design
Week 21 | Tender Presentation Writing | Individual Work | Marketing | 2 | 2
Week 21 | Finalising Logo Designs | Individual Work | Marketing | 1 | 1
Week 21 | Tender Presentation Writing | Individual Work | Marketing | 2 | 2
Week 21 | Tender Presentation Writing | Individual Work | Marketing | 3 | 3
Week 23 | Group Practical Session | Individual Work | Development - Client Software | 1 | 1
Week 23 | Group Practical Session | Individual Work | Development - Client Software | 1.5 | 1.5
Week 24 | Group Practical Session | Individual Work | Marketing | 1 | 1
Week 33 | Group Practical Session | Meeting | Development - Client Software | 1 | 1
Week 34 | Map Theme Programming | Individual Work | Development - Client Software | 1.5 | 1.5
Week 35 | Map Theme Programming | Individual Work | Development - Client Software | 2 | 2
Week 35 | Group Practical Session | Meeting | Marketing | 1.5 | 3 | Added Design and Marketting Team Role Review for QA
Week 33 | Map Theme Programming | Individual Work | Development - Client Software | 1 | 1
Week 35 | Map Theme Programming | Individual Work | Development - Client Software | 2.5 | 2.5
Week 35 | Group Practical Session | Individual Work | Marketing | 3 | 3 | Working on example problems for speech/presentation
Week 35 | Group Practical Session | Individual Work | Marketing | 3 | 3 | Further work on example problems
Week 35 | Presentation Work | Individual Work | Marketing | 2.5 | 2.5 | Creating mockups for example problems
Week 36 | Group Practical Session | Individual Work | Marketing | 3 | 3 | Value proposition details and start on social proof
Week 36 | Presentation Work | Individual Work | Marketing | 0.75 | 0.75 | Creating last mock up for example problems
Week 36 | Group Practical Session | Individual Work | Marketing | 3 | 3 | Social proof slide and statistics
Week 36 | Group Practical Session | Individual Work | Marketing | 2.5 | 1.75 | Photo shoot took a little long
Week 36 | Presentation Work | Individual Work | Marketing | 0.5 | 0.5 | Quick few things
Week 36 | Group Photos ☠☠☠☠ | Individual Work | Marketing | 1 | 1
Week 36 | Presentation Work | Individual Work | Marketing | 3 | 3 | Mock ups for mobile app + fixes
Week 36 | Group Practical Session | Individual Work | Marketing | 1.5 | 1.5 | Marketing and business plan ideas
Week 36 | Presentation Work | Individual Work | Marketing | 1.5 | 1.5 | Marketing and business plan added section on internation stuffs
Week 36 | Presentation Work | Individual Work | Marketing | 0.5 | 0.5 | Quick presentation fixes
Week 36 | Presentation Work | Individual Work | Marketing | 1.25 | 1.25 | Some additions ig lol
Week 37 | Last minute clean ups | Individual Work | Marketing | 1.25 | 1.25 | Clean up drive slightly, adjust pics, QA
Week 37 | Final Sales Presentation | Meeting | Marketing | 3 | 3 | Included preparation before hand for a few hours and final presentation

## Fraser
Week | Description | Category | Area of Development | Est. Hours | Hours | Notes
Week 21 | Implement GribBagLayout so that Slides will resize the elements it contains automatically | Individual Work | Development - Client Software | 1.5 | 1.5 | Made everyone else on the client side development's life easier
Week 21 | Initial creation of Acceptance Criteria for inter group contract | Individual Work | Contracts | 1 | 1
Week 21 | Finishing acceptance criteria | Individual Work | Contracts | 1 | 0.75 | Man I hate the other group for rushing this
Week 21 | Updated Contract to prevent Guisseppe from throwing his toys out of the pram | Individual Work | Contracts | 0.5 | 0.5 | Needed to do some research on Optionals in Java
Week 21 | Adding missing tests to "Slide" and "PresElement" | Individual Work | Development - Client Software | 1 | 1 | I forgot to add JUnit tests to these
Week 21 | Creating the project file and Github for the contract | Individual Work | Contracts | 0.5 | 0.75 | GitHub wont let you upload (via the browser) all the project files as they are hidden so I had to re-create the project and do it via terminal
Week 21 | Added fixed aspect ratio to slides in a Presentation | Individual Work | Development - Client Software | 0.5 | 0.5 | Pretty Simple like
Week 21 | Found Slide is terrible & doesn't work at high resolutions -> tried to fix | Individual Work | Development - Client Software | 0.5 | 3 | GridBagLayout is wack as fuck and I hate it so much, why did I subject myself and the team to this? Basically, to get empty cells (needed for the correct layout to show) you need to add glue to EVERY CELL, this means when the resolution is like above 500x500, java poos itself and stops working at all cuz it takes too long to RENDER INVISABLE OBJECTS
Week 21 | Finally Fixed slide & failing tests in Presentation | Individual Work | Development - Client Software | 3 | 3 | Had to implement a custom LayoutManager in Slide to set the bounds of each PresElement
Week 21 | Fixed failing tests in Presentation | Individual Work | Development Testing
Week 21 | Started work on the Integration & Testing plan | Individual Work | Integration and Testing | 1.5 | 1.5 | Mate this is actually fucked. May have to restructure all of the plan again to get this to be legit
Week 22 | Edited Acceptance criterea | Individual Work | Contracts | 0.25 | 0.25 | Added the inclusion of the Presentation class
Week 22 | Tender Pres | Meeting | Marketing | 1 | 1 | This should have beem
Week 22 | Starting work on MapScene and mapping package | Individual Work | Development - Client Software | 3 | 3.25 | Mostly finished this. All tests still to be written (Whoopsies) -> realiant on some server interaction
Week 22 | Fixing git with other group | Individual Work | Contracts | 0.25 | 0.25 | Git was being wack and refusing to add the needed files
Week 22 | finishing up on mapping and testing | Individual Work | Development Testing | 2 | 2 | no tests for heatmap as ive got no clue how to do that
Week 22 | Integration and testing plan meeting | Meeting | Integration and Testing | 1 | 1.25
Week 22 | Group Session: merge Presentation, merge mapping edit UML diagram | Individual Work | Development - Client Software | 2 | 2
Week 23 | Creation of Client Version Number list and update to UML Diagram for I&T plan | Individual Work | Integration and Testing | 1.5 | 1.5 | Just getting stuff done for pauly P
Week 23 | Planing for XML parsing algorthm | Individual Work | Development - Client Software | 0.25 | 0.25 | this should get added to the task below
Week 23 | Created XML Parser | Individual Work | Development - Client Software | 3 | 3.25 | Took a bit longer cuz im super hungover and stayed up to 7 am doing some "sports"
Week 23 | Weeky Sweng Lab session: Talking to the team about progress/ helping to fix issues | Meeting | Development - Client Software | 1.5 | 1.25 | I was late
Week 23 | Inital set up of Android studio and project within | Individual Work | Contracts | 0.25 | 0.25 | Pretty cool looking IDE
Week 23 | Tweak to VideoPlayer in prep for merge | Individual Work | Integration and Testing | 0.75 | 0.75 | Will writes pretty sexy tests
Week 24 | Initial implementation of Contracted work - ImageElement | Individual Work | Contracts | 1.5 | 1.5 | Need to add timers and tests
Week 24 | Review and merge of ImageElement for our client | Individual Work | Development - Client Software | 0.5 | 0.5 | Big ups luke george
Week 24 | Completion of contract with testing | Individual Work | Contracts | 2 | 2.5 | Man got some weird bugs that took way to long to figure out
Week 25 | Creation of mainScene for first iteration | Individual Work | Development - Client Software | 3 | 3 | man some of these scenes are wack as fuck. Would have been dank of stuart to show up to java labs last year so that people weren't just mashing thier keyboards
Week 25 | Fixing the ImageElement submission | Individual Work | Contracts | 1 | 1 | Maybe if I spent the time i was planning on working on this last thursday programming rather than fucking i would have actually been bothered to refactor sophies submission but atleast we still got the early accetance for the image one which was more money
Week 25 | Integration and testing plan work | Individual Work | Integration and Testing | 0.5 | 0.5 | Chat will Willy H and Pauly P. What a lovely time
Week 25 | Testing and Integration Plan review | Individual Work | Integration and Testing | 0.5 | 0.5 | Made a few grammar corrections but Willy H and Pauly. P have banged this one out of the park. If i could have sex with a document, I would give our testing and integration plan enthusiastic consent!
Week 31 | Leadership meeting after easter | Meeting | Development - Client Software | 1.25 | 1.25 | Nice catch up with the gang, refresh for new term
Week 31 | Added pxToPt function to slide & code review | Individual Work | Development - Client Software | 1 | 0.75 | Also need to review some of the code written over easter
Week 33 | Group meeting | Meeting | Development - Client Software | 1 | 1
Week 34 | Group meeting | Meeting | Development - Client Software | 1 | 3 | Have to discus group restructure for finishing the project
Week 35 | Approval & merge of Server | Individual Work | Integration and Testing | 0.25 | 0.25 | Paul actually knows what he is doing
Week 35 | Group programming session | Individual Work | Development - Client Software | 3 | 3 | Trying to fix mapscene errors
Week 35 | Group Programming session | Individual Work | Development - Client Software | 3 | 3 | mixed mapscene error and started to fix presentation parser
Week 36 | Group Programming session | Individual Work | Development - Client Software | 3 | 3 | Fixed Presentation Parser, changed the directory of map caches and fixed ImageViewer issues and merged all that to main
Week 36 | Group Programming Session | Individual Work | Development - Client Software | 3 | 3.5 | Added overlay to presentation and additional comments/refactoring to other media elements
Week 36 | Group Programming Session | Individual Work | Development - Client Software | 3 | 3.5 | Worked on sorting out mainScene and started sotred out optionsScene
Week 36 | Group Programming Session | Individual Work | Development - Client Software | 3 | 4 | Added Rounded button to add changes to optionsScene
Week 36 | Group Programming Session | Individual Work | Development - Client Software | 3 | 3.5 | Stating to fix the dreaded sidebarScene
Week 36 | Solo Programming Session (other than Jon) cuz for some reason nobody showed up to finish the client 2 DAYS BEFORE THE DEMONSTRATION (Sri was here but literally did fuck all) | Individual Work | Development - Client Software | 3 | 8.75 | Oh sweet Jeeesus. SidebarScene is finally completed and useable in an application rather than in one specific view on one specific laptop.... Oh lord my eyes hurt
Week 36 | Final Iteration crunch | Individual Work | Development - Client Software | 3 | 16 | OH MY GOODNESS. This was rough but worth it.Shout out paul for staying till 2 but Jon Cooke is one dedicated man, staying in uni till 6 to get it working perfectly
Week 37 | Final Presentation | Individual Work | Development - Client Software | 1 | 1 | Banged it out of the park
Week 37 | Final Documentation Sort out | Individual Work | Documentation | 4 | 2 | This was not as bad as i though
Week 37 | Final Code sort out | Individual Work | Development - Client Software | 4 | 8 | Like wow there was a lot of stuff to be removed that never ran, very few people had added author titles and SO MUCH LINTING TO REMOVE SIMPLE WARNINGS. Also I sorted out a better way of using constants.

## CALCULATIONS
Employee | Individual Hours | Meeting Hours | Total Hours | Individual Labour Costs (£) | Meeting Labour Costs (£) | Total Labour Costs (£) | Actual | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Jonathan | 121.75 | 11.25 | 133 | 1521.875 | 140.625 | 1662.5 | Development - Client Software | 12.5 | 10.25 | 13.25 | 12.75 | 15.75 | 14 | 0 | 0 | 13 | 5.25 | 4 | 2 | 19.25 | 11 | 41.5 | 116.25 | 23 | 0 | 0
Luke | 32.25 | 6 | 38.25 | 403.125 | 75 | 478.125 | Development - Server Software | 5.5 | 3 | 7.75 | 4.75 | 6.5 | 0 | 0 | 0 | 8.5 | 3.25 | 2 | 1 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0
Will | 25.25 | 15.5 | 40.75 | 315.625 | 193.75 | 509.375 | Development Testing | 2 | 2 | 1 | 5.75 | 2.5 | 0 | 0 | 0 | 4.5 | 4 | 8 | 0.5 | 0 | 0 | 0 | 3.75 | 8 | 0 | 0
Srikanth | 60.5 | 8.5 | 69 | 756.25 | 106.25 | 862.5 | Integration and Testing | 4 | 6.25 | 10 | 1 | 5.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 2.5 | 0 | 0.75 | 0 | 0 | 0 | 0
Sophie | 75 | 14.5 | 89.5 | 937.5 | 181.25 | 1118.75 | Documentation | 11.25 | 6 | 6.5 | 2.5 | 14 | 0 | 0 | 0 | 0 | 11.5 | 15.75 | 6.25 | 2.5 | 2 | 38.5 | 21.5 | 52.75 | 0 | 0
Oliver | 22 | 11.5 | 33.5 | 275 | 143.75 | 418.75 | Marketing | 29.5 | 12 | 0.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | 3.5 | 10 | 0 | 0.5 | 0 | 23.75 | 60.75 | 16.5 | 0 | 0
Matteo | 44.5 | 18.25 | 62.75 | 556.25 | 228.125 | 784.375 | Finance | 7.5 | 2.5 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0.25 | 1 | 4 | 4.75 | 5 | 13 | 0 | 0 | 0 | 0
Paul | 95.5 | 7.25 | 102.75 | 1193.75 | 90.625 | 1284.375 | Contracts | 3 | 0.5 | 9.25 | 6.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidharth | 87.25 | 23.75 | 111 | 1090.625 | 296.875 | 1387.5 | Expected
Sarujan | 49.5 | 7 | 56.5 | 618.75 | 87.5 | 706.25 | Development - Client Software | 4.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fraser | 97 | 8.75 | 105.75 | 1212.5 | 109.375 | 1321.875 | Development - Server Software | 5.5 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 710.5 | 132.25 | 842.75 | 8881.25 | 1653.125 | 10534.375 | Development Testing | 10 | 10.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Integration and Testing | 0 | 0 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Documentation | 8.25 | 5.25 | 4.25 | 6.25 | 6.25 | 5.25 | 4.75 | 3.25 | 5.25 | 7.75 | 11.25 | 7.25 | 9.25 | 8.25 | 7.25 | 8.25 | 9.25 | 0 | 0
[7 empty] | Marketing | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 10 | 0 | 0 | 0 | 0 | 0
[7 empty] | Finance | 3 | 5 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 5 | 3 | 3 | 7 | 1 | 1 | 0 | 0
[7 empty] | Contracts | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Hours since new loan |  |  | 421.5 |  | /389

## BACKEND (hidden)
Jonathan | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 0 | 2 | 0 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.75 | 1 | 0 | 0
Development - Server Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 0
Integration and Testing | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 2 | 3 | 0 | 1 | 5 | 0 | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 2 | 26 | 12.75 | 26.25 | 0 | 0
Marketing | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Luke | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 0 | 0 | 0.75 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 4.5 | 17.5 | 0 | 0 | 0
Development - Server Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 0 | 0 | 1 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration and Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing | 0 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Finance | 7 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Will | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 0.5 | 0 | 5.25 | 2 | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.75 | 0 | 3 | 0 | 0 | 0 | 0
Development - Server Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0
Integration and Testing | 0 | 3 | 0.75 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 2 | 0 | 0.5 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.75 | 2 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Srikanth | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 7.5 | 21 | 5 | 0 | 0
Development - Server Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration and Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 4 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 7 | 3 | 1.5 | 0 | 1 | 0 | 0 | 0 | 0
Marketing | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sophie | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 2 | 0 | 0 | 2 | 0 | 9 | 0 | 0 | 13 | 5.25 | 2 | 0 | 1.5 | 4 | 0 | 2 | 0 | 0 | 0
Development - Server Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration and Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing | 7.5 | 1 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 1.75 | 0 | 0 | 0.5 | 0 | 4 | 20.5 | 1.5 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oliver | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 1 | 2 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
Development - Server Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration and Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing | 5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 7.5 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Matteo | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Development - Server Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration and Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0.75 | 0 | 0 | 2 | 4 | 1.5 | 0 | 0
Marketing | 4.25 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 13 | 2.25 | 0 | 0
Finance | 0.5 | 2.25 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0.5 | 3.5 | 3 | 1.5 | 12.5 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Paul | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 14 | 12.75 | 8 | 0 | 0
Development - Server Software | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 4.5 | 4 | 8 | 0.5 | 0 | 0 | 0 | 0 | 5 | 0 | 0
Integration and Testing | 2.5 | 1 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 1.5 | 0 | 6.5 | 1 | 5.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 3.25 | 0 | 0
Marketing | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sidharth | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Development - Server Software | 2.5 | 2 | 7.75 | 4.75 | 6.5 | 0 | 0 | 0 | 8.5 | 1.75 | 2 | 1 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0
Development Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration and Testing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 3.25 | 0 | 0 | 0.5 | 0.25 | 0 | 0 | 0 | 0 | 6.5 | 2 | 2 | 1 | 0 | 9.5 | 4.75 | 19.75 | 0 | 0
Marketing | 1.25 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.25 | 7.5 | 4 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 1.5 | 0.5 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sarujan | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1.5 | 4.5 | 0 | 0 | 0 | 0
Development - Server Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration and Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Marketing | 11.5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5 | 17.75 | 4.25 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fraser | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39
Development - Client Software | 9 | 5.25 | 4.75 | 0.5 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 3 | 6 | 42.25 | 9 | 0 | 0
Development - Server Software | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Development Testing | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integration and Testing | 1.5 | 1.25 | 2.25 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0
Documentation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0
Marketing | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contracts | 3 | 0.5 | 0.25 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0